## Settings
Settings | [10 empty] | Gantt
Project Details |  |  | Project Role Types |  |  |  | Project Role Types
| Project Title: | Example Project |  | Role | Code | # |  | Name | Role | Code
|  |  |  | Project Management | PM | 1 |  | C. Miller | Coding | COD
| Project Manager: | C. Miller |  | Coding | COD | 2 |  | T. Suarez | Project Management | PM
|  |  |  | Design | DES | 0 |  | C. Anthony | Marketing | MAR
| Project Priority: | High |  | Marketing | MAR | 1 |  | N. Manson | Finance | FIN
|  |  |  | Finance | FIN | 1 |  | J. Griffin | Coding | COD

## Gantt
Example Project | [20 empty] | Project Timespan: | [7 empty] | 2025-02-05 |  |  |  |  | - | 2025-03-17 |  |  |  |  | (29) |  |  | Project Manager: | [6 empty] | C. Miller | [7 empty] | Settings
| Input Column | [19 empty] | Color By | [8 empty] | Display | [8 empty] | Show Progress | [18 empty] | Highlight
| Calculated Column | [19 empty] | Project Structure | [8 empty] | Plan | [8 empty] | No | [18 empty] | Today
Snapshot Column
⚠-🏴-◆-↖-↙ | [7 empty] | Actual Plan | [9 empty] | Base Plan |  | Today | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-31 | 2025-04-01 | 2025-04-02
[8 empty] | Updated on: | [9 empty] | Saved on: |  | 0
ids |  |  | Item Details |  |  |  |  | 2025-02-19 | [9 empty] | 2025-02-19
id | s id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | ind. End | d. id | d. item |  | d. conn | d. lag | Work Days | Start | End | Start | End | % | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W
1 | 1 | -1 | S | Planning |  |  | ⚠ | 2025-02-05 |  |  |  |  | FS |  | 10 | 2025-02-05 | 2025-02-18 | 2025-01-17 | 2025-01-30 | 46% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | 2 | T | Task P1 | COD | C. Miller |  | 2025-02-05 |  |  |  |  | FS |  | 5 | 2025-02-05 | 2025-02-11 | 2025-01-17 | 2025-01-23 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | 1 | T | Task P2 | PM | T. Suarez | ⚠ |  |  | 2 | ↖ | (T)Task P1 | FS |  | 3 | 2025-02-12 | 2025-02-14 | 2025-01-24 | 2025-01-28 | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 5 | T | Task P3 | FIN | N. Manson | ⚠ |  |  | 3 | ↖ | (T)Task P2 | FS |  | 2 | 2025-02-17 | 2025-02-18 | 2025-01-29 | 2025-01-30 | 90% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1 | 1 | M | Milestone I | PM | T. Suarez |  |  |  | 4 | ↖ | (T)Task P3 | FF |  |  | 2025-02-18 | 2025-02-18 | 2025-01-30 | 2025-01-30 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2 | -1 | S | Implementation | MAR | C. Anthony |  | 2025-02-19 |  |  |  |  | FS |  | 10 | 2025-02-19 | 2025-03-04 | 2025-01-31 | 2025-02-13 | 13% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 2 | 1 | T | Task P1 | PM | T. Suarez |  |  |  | 1 | ↖ | (S)Plannin… | FS |  | 5 | 2025-02-19 | 2025-02-25 | 2025-01-31 | 2025-02-06 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2 | 4 | T | Task P2 | MAR | C. Anthony |  |  |  | 7 | ↖ | (T)Task P1 | FS |  | 3 | 2025-02-26 | 2025-02-28 | 2025-02-07 | 2025-02-11 | 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | 5 | T | Task P3 | FIN | N. Manson |  |  |  | 8 | ↖ | (T)Task P2 | FS |  | 2 | 2025-03-03 | 2025-03-04 | 2025-02-12 | 2025-02-13 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2 | 2 | M | Milestone II | COD | J. Griffin |  |  |  | 9 | ↖ | (T)Task P3 | FF |  |  | 2025-03-04 | 2025-03-04 | 2025-02-13 | 2025-02-13 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 3 | -1 | S | Rollout Prep |  |  |  | 2025-02-18 |  |  |  |  | FS |  | 11 | 2025-02-18 | 2025-03-04 | 2025-01-30 | 2025-02-13 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 3 | -1 | T | Task RP1 | [5 empty] | 13 | ↙ | (T)Task RP… | SF |  | 5 | 2025-02-18 | 2025-02-24 | 2025-01-30 | 2025-02-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3 | -1 | T | Task RP2 | [5 empty] | 14 | ↙ | (T)Task RP… | SF |  | 4 | 2025-02-25 | 2025-02-28 | 2025-02-06 | 2025-02-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3 | -1 | T | Task RP3 | [5 empty] | 15 | ↙ | (M)Milesto… | FF |  | 2 | 2025-03-03 | 2025-03-04 | 2025-02-12 | 2025-02-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 3 | -1 | M | Milestone III | [5 empty] | 6 | ↖ | (S)Impleme… | FF |  |  | 2025-03-04 | 2025-03-04 | 2025-02-13 | 2025-02-13 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 4 | -1 | S | Rollout |  |  |  | 2025-03-05 |  |  |  |  | FS |  | 9 | 2025-03-05 | 2025-03-17 | 2025-02-14 | 2025-02-26 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 4 | -1 | T | Task RP1 | [5 empty] | 11 | ↖ | (S)Rollout… | FS |  | 3 | 2025-03-05 | 2025-03-07 | 2025-02-14 | 2025-02-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 4 | -1 | T | Task RP2 | [5 empty] | 17 | ↖ | (T)Task RP… | FS |  | 3 | 2025-03-10 | 2025-03-12 | 2025-02-19 | 2025-02-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 4 | -1 | T | Task RP3 | [5 empty] | 18 | ↖ | (T)Task RP… | FS |  | 3 | 2025-03-13 | 2025-03-17 | 2025-02-24 | 2025-02-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 4 | -1 | M | Milestone IV | [5 empty] | 19 | ↖ | (T)Task RP… | FF |  |  | 2025-03-17 | 2025-03-17 | 2025-02-26 | 2025-02-26 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 5 | -1 | S | [9 empty] | FF |  |  |  |  | 2025-02-26 | 2025-02-26 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0